## Sheet1
GANTT Chart - C8506 Final Project
Milestones |  | Week 1 (09.22.14) | Week 2 | Week 3 | Week 4 | Week 5 (10.20.14) | Week 6 | Week 7 (11.03.14) | Week 8 | Week 9 | Week 10 | Week 11 & 12 (12.01.14)
Components
Milestone #1 | Preliminary Design Work
Task Assignments
Test Cases
Milestone #2 | Client - Commander Mode
Client - Listening Mode
Server - Listen for Cmds
Server - Rtn. Cmd. Results
Milestone #3 | Client - Data Encryption
Client - Covert Channels
Server - Data Encryption
Server - Covert Channels
Milestone #4 | Client - Port Knocking
Server - Port Knocking
Client - Config File
Milestone #5 | Server - File Monitoring
Milestone #6 | Server - Exfiltration
Client - Parse Exfiltration
Testing Documentation
Milestone #7 | Finalize Documentation
README