## Sheet1
Team Members | Project Tasks & Responsibilities | Scheduled Date of Completion
David Tran | Preliminary Design Work | Week 7 (11.03.14)
| Task Assignments | Week 1 (09.22.14)
| Test Cases | Week 12 (12.08.14)
| Client - Commander Mode | Week 2
| Client - Listening Mode | Week 2
| Client - Data Encryption | Week 3
| Client - Covert Channels | Week 3
| Testing & Finalizing Documentation | Week 12 (12.08.14)
Cole Rees | Server - Listen for Commands | Week 2
| Server - Return Command Results | Week 2
| Server - Data Encryption | Week 3
| Server - Covert Channels | Week 3
| Port Knocking | Week 5 (10.20.14)
| Configuration File | Week 7 (11.03.14)
| File Monitoring | Week 7 (11.03.14)
| Exfiltration | Week 10
| README | Week 12 (12.08.14)